## TASK tracker
Project Stage | Task Title | Description | Assigned To | Status | Start Date | Due Date | Critical? | Source Link | Actual Days Taken for completion | Sort order
2. Design | Task tracker organization | Make sure all task tracker is updated. | Kai Dolan | Done | 2026-09-03 | 2026-09-07 | TRUE |  |  | 3
2. Design | ISO CAN Transceiver system design | Table of Jetson CAN Com information | Dexi Li | In Progress | 2026-09-01 | 2026-09-06 | FALSE | 1. DEXI - Electrical System Brief 2. Design manual ISO CAN Texas Instrument |  | 1
|  | Table of Wheel motor CAN information (AK10-9 v2.0) + Datasheet linked + Add to drive |  |  | 2026-09-02 | 2026-09-08 | FALSE
|  | Table: Robot Arm CAN information (Link+drive) |  |  | 2026-09-03 | 2026-09-08 | FALSE
|  | Record the arm length, bus cable length (at least the estimated) |  |  | 2026-09-04 | 2026-09-09 | FALSE
|  | Calculate maximum stub length (if possible) |  |  | 2026-09-05 | 2026-09-10 | FALSE
|  | Find the cable link (shielded) + Note: Avoid close to the battery |  |  | 2026-09-06 | 2026-09-11 | FALSE
|  | How much propagation delay it has (optional, if not possible, try simulation) |  |  | 2026-09-07 | 2026-09-12 | FALSE
|  | Solution would prob be ISOW1050 or 1044, so check compatibility and make decision (Make a comparison table) |  |  | 2026-09-08 | 2026-09-13 | FALSE
|  | Check what requirements is needed for the ISOW. For POWER: Input voltage, worst case voltage and current, inrush behaviour?, isolated voltage output, efficiency affected?, ripple? any other components required (thermal control, capacitance) - Working isolation voltage, rating, isolation barrier capacitance. |  |  | 2026-09-09 | 2026-09-14 | FALSE
|  | What pins there are, start simulation (Psice) Check: - TXD dominant timeout - Undervoltage? - Undervoltage lockout - Fail-safe recessive bus rate - Standby control - Remote wakeup? - Predictable state while Jetson boots - Predictable state when 3.3V/5V power up in different sequences |  |  | 2026-09-10 | 2026-09-15 | FALSE
|  | Make BOM |  |  | 2026-09-11 | 2026-09-16 | FALSE
|  | PCB checked by Rid and Tom? |  |  | 2026-09-12 | 2026-09-17 | FALSE
|  | Order |  |  | 2026-09-13 | 2026-09-18 | FALSE
1. Investigation | Components list | Create document with full components list of all subsystems, split into parts that can be reused and parts that will need to be bought | Dexi Li Kai Dolan | Not Started | 2026-09-03 | 2026-09-13 | FALSE |  |  | 1
6. Inspection & Testing | CAN Hub 25/26 Testing | Assemble the CAN Hub PCB from 25/26, and verify the design by creating and documenting a test procedure. | Thomas A Haley | In Progress | 2026-08-31 | 2026-10-01 | FALSE |  |  | 1
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
[7 empty] | FALSE |  |  | 2
8. Documentation | Complete finance tracker | Fill in all components on the finance tracker spreadsheet. Verify quantity of each component and total cost. | Dexi Li Kai Dolan | Done | 2026-08-31 | 2026-08-24 | TRUE | Finance Planner |  | 3
8. Documentation | Team Development Doc | Complete lessons learned from last year section on Tab 1 development plan doc | Kai Dolan | Done | 2026-08-23 | 2026-08-26 | TRUE | Electrical Team Development Plan |  | 3
8. Documentation | Team Development Doc | Complete components list | Dexi Li | Done | 2026-08-24 | 2026-08-28 | FALSE | Electrical Team Development Plan |  | 3
1. Investigation | Set up meeting with electronics team | Reach out to Harry and Ali to set up an online meeting to discuss possible roles | Kai Dolan | Done | 2026-08-26 | 2026-08-31 | FALSE |  |  | 3
1. Investigation | Mini-rover research | Research mini-rover electrical development from last year to see what roles could suit the new joiners | Kai Dolan | Done | 2026-08-26 | 2026-09-01 | FALSE |  |  | 3
8. Documentation | Meeting with Ali, Harry | Make a presentation for Ali, Harry: introduction, team planning, roles, and answer their questions | Dexi Li Kai Dolan | Done | 2026-09-02 | 2026-09-03 | FALSE | Electronics - Meeting Docs - 26/27 |  | 3
1. Investigation | Design technical questions | Design technical questions for electrical team interviews. Can be tested on Kai to see if they're suitable | Dexi Li | Done | 2026-08-26 | 2026-09-03 | FALSE | Electrical Team Development Plan | 1 Day | 3

## Progress Dashboard
Team Progress Dashboard
1. METRICS BY PROJECT STAGE
Project Stage | Total Tasks | Completed Tasks | Completion % | Avg Days to Complete
1. Investigation | 4 | 3 | 75% | 0
2. Design | 2 | 1 | 25% | 0
3. Prototype | 0 | 0 | 0% | 0
4. Order | 0 | 0 | 0% | 0
5. Construction | 0 | 0 | 0% | 0
6. Inspection & Testing | 1 | 0 | 0% | 0
7. Improvement | 0 | 0 | 0% | 0
8. Documentation | 4 | 4 | 100% | 0
2. TEAM MEMBER WORKLOAD & PERFORMANCE
Team Member | Assigned Tasks | Completed Tasks | Remaining Tasks | Delayed Tasks Warning
Dexi Li | 3 | 2 | 1 | 0
Kai Dolan | 3 | 3 | 0 | 0
harry | 0 | 0 | 0 | 0
Ali | 0 | 0 | 0 | 0
Thomas A Haley | 1 | 0 | 1 | 0
3. ATTENTION REQUIRED
Total Project Task Blocked! | 0
Total Tasks Unassigned | 0