## Leadership and Milestones
Tasks | Assignee | Start Date | End Date | Status | Notes
Sub-Team Dev Plans | Sub-Team Leads | 2026-08-17 | 2026-09-14 | Complete
Create Application Form | Executive Team | 2026-09-07 | 2026-09-20 | In-Progress
Advertise Drone and Mini-Rover Lead Positions | Executive Team | 2026-09-14 | 2026-09-28 | Not Started | Not sure when to end this
Advertise Applications | Executive Team | 2026-09-21 | 2026-10-12 | Not Started | Leaving at least two weeks for sub-team leads to organise and carry out interviews
Create Technical Questions For Application Form | Sub-Team Leads | 2026-09-12 | 2026-09-18 | In-Progress
Interview Stage | All Leadership | 2026-09-21 | 2026-11-01 | Not Started
Prepare Onboarding | Sub-Team Leads & Chief Engineer | 2026-09-07 | 2026-09-21 | Not Started
Design Phase | Sub-Teams | 2026-11-01 | 2026-12-31 | Not Started | Start and end date TBD
Milestone: Teams Ready For Design Phase |  | 2026-11-01 | 2026-11-01 | Milestone
Milestone: ARC Video Submissions Open |  | 2027-02-15 | 2027-02-15 | Milestone
Milestone: ARC Early Video Deadline |  | 2027-03-15 | 2027-03-15 | Milestone
Milestone: ARC Late Video Deadline |  | 2027-04-15 | 2027-04-15 | Milestone
Milestone: Everything ordered by this date in prep for video submission |  | 2027-01-31 | 2027-01-31 | Milestone

## Drone Tasks
Tasks | Assignee | Start Date | End Date | Status | Notes

## Elec Tasks
Tasks | Assignee | Start Date | End Date | Status | Notes

## Mech Tasks
Tasks | Assignee | Start Date | End Date | Status | Notes

## Mini Tasks
Tasks | Assignee | Start Date | End Date | Status | Notes

## Robotics Tasks
Tasks | Assignee | Start Date | End Date | Status | Notes

## Sci Tasks
Tasks | Assignee | Start Date | End Date | Status | Notes

## Software Tasks
Tasks | Assignee | Start Date | End Date | Status | Notes
Handover and Planning |  | 2026-08-01 | 2026-09-27 | In-Progress
Plan and Create Documents for New Members (First Tasks) |  | 2026-09-01 | 2026-09-27 | In-Progress
Repo Setup with Claude |  | 2026-09-21 | 2026-09-27 | Not Started
Get Chassis Plans from Mechanical Team |  | 2026-09-28 | 2026-10-04 | Not Started
Advertising Software Team at Lectures |  | 2026-09-28 | 2026-10-09 | Not Started
Interviews |  | 2026-09-28 | 2026-11-01 | Not Started
Onboarding |  | 2026-10-19 | 2026-11-08 | Not Started
Create URDF Model of Rover |  | 2026-11-02 | 2026-11-09 | Not Started
Update software/autonomous code to accomodate for Lunabotics |  | 2026-11-02 | 2026-12-20 | Not Started
Purchase sem 1 items |  | 2026-11-02 | 2026-11-15 | Not Started
Setup 5GHz/2.4GHz PtP network |  | 2026-11-23 | 2026-11-29 | Not Started
Build existing rover |  | 2026-09-28 | 2026-11-01 | Not Started
Test and refine autonomous navigation simulation |  | 2026-11-30 | 2027-02-14 | Not Started
Get complete chassis from mechanical team |  | 2027-02-01 | 2027-02-07 | Not Started
Make new rover model in Gazebo |  | 2027-02-01 | 2027-02-07 | Not Started
Amend code in simulation to perform correctly with new rover model |  | 2027-02-08 | 2027-02-14 | Not Started
Amend autonomous nav code in sim for ARC missions |  | 2027-02-15 | 2027-03-21 | Not Started
Start testing autonomous nav on physical rover, consult other sub-teams |  | 2027-03-01 | 2027-06-27 | Not Started
Test new backup network |  | 2027-03-01 | 2027-06-27 | Not Started