## Gantt Chart
GANTT CHART | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Mech Team |  |  |  |  | COMPANY NAME | [6 empty] | Marsworks
PROJECT MANAGER |  | Daniel Parkus |  |  |  |  | DATE | [6 empty] | 2026-08-24
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PRE PHASE ONE | [24 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | 24/08 - 28/08 |  |  |  |  | 31/08 - 04/09 |  |  |  |  | 07/09 - 11/09 |  |  |  |  | 14/09 - 18/09 |  |  |  |  | 21/09 - 25/09 |  |  |  |  | 28/09 - 02/10 |  |  |  |  | 05/10 - 09/10 |  |  |  |  | 12/10 - 16/10 |  |  |  |  | 19/10 - 23/10 |  |  |  |  | 26/10 - 30/10 |  |  |  |  | 02/11 - 06/11 |  |  |  |  | 09/11 - 13/11 |  |  |  |  | 16/11 - 20/11 |  |  |  |  | 23/11 - 27/11 |  |  |  |  | 30/11 - 04/12 |  |  |  |  | 07/12 - 11/12 |  |  |  |  | 14/12 - 18/12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Management
1.1 | Budget Estimate | Daniel | 2026-08-24 | 2026-08-25 | 1 | 100% | bar: 24/08 - 28/08 M
1.2 | Create Project Plan | Daniel | 2026-08-24 | 2026-09-25 | 31 | 25% | bar: 24/08 - 28/08 M to 21/09 - 25/09 F
1.3 | Update CAD Model | Daniel | 2026-09-21 | 2026-10-02 | 11 | 0% | bar: 21/09 - 25/09 M to 05/10 - 09/10 F
1.4 | Recruitment | Daniel | 2026-10-05 | 2026-10-31 | 26 | 0% | bar: 05/10 - 09/10 M to 26/10 - 30/10 F
2 | Rover Testing & Validation
2.1 | Inspect Rover | Team | 2026-09-21 | 2026-09-25 | 4 | 0% | bar: 21/09 - 25/09 M to 21/09 - 25/09 F
2.2 | Drive Testing | Team | 2026-09-28 | 2026-10-09 | 11 | 0% | bar: 28/09 - 02/10 M to 05/10 - 09/10 F
2.3 | Suspension Testing | Team | 2026-09-28 | 2026-10-09 | 11 | 0% | bar: 28/09 - 02/10 M to 05/10 - 09/10 F
2.4 | Excavator Testing | Team | 2026-09-28 | 2026-10-09 | 11 | 0% | bar: 28/09 - 02/10 M to 05/10 - 09/10 F
2.5 | Hopper Testing | Team | 2026-09-28 | 2026-10-09 | 11 | 0% | bar: 28/09 - 02/10 M to 05/10 - 09/10 F
2.6 | Issue Log | Team | 2026-10-08 | 2026-10-09 | 1 | 0%
3 | Pivot Wheel Project
3.1 | Research concepts | Daniel | 2026-10-05 | 2026-10-07 | 2 | 0%
3.2 | CAD design | Daniel | 2026-10-07 | 2026-10-13 | 6 | 0% | bar: 05/10 - 09/10 M to 12/10 - 16/10 T
3.3 | Design review | Daniel | 2026-10-13 | 2026-10-14 | 1 | 0% | bar: 12/10 - 16/10 T to 12/10 - 16/10 W
3.4 | Prototype manufacture | Daniel | 2026-10-15 | 2026-11-06 | 21 | 0% | bar: 12/10 - 16/10 R to 02/11 - 06/11 F
3.5 | Prototype testing | Daniel | 2026-10-30 | 2026-11-27 | 27 | 0% | bar: 26/10 - 30/10 F to 23/11 - 27/11 F
3.6 | Final CAD release | Daniel | 2026-11-30 | 2026-12-11 | 11 | 0% | bar: 30/11 - 04/12 M to 07/12 - 11/12 F
4 | Hopper Redesign
4.1 | Requirements | Matt |  |  | 0 | 0%
4.2 | CAD | Matt |  |  | 0 | 0%
4.3 | Prototype | Matt |  |  | 0 | 0%
4.4 | Testing | Matt |  |  | 0 | 0%
5 | Excavator Repair
5.1 | Failure investigation | Owen & Jack |  |  | 0 | 0%
5.2 | Redesign | Owen & Jack |  |  | 0 | 0%
5.3 | Manufacture | Owen & Jack |  |  | 0 | 0%
5.4 | Testing | Owen & Jack |  |  | 0 | 0%
6 | Manufacturing
6.1 | Manufacture pivot wheels | Daniel |  |  | 0 | 0%
6.2 | Manufacture hopper | Matt |  |  | 0 | 0%
6.3 | Manufacture excavator parts | Owen & Jack |  |  | 0 | 0%
6.4 | Manufacture drill guides | Team |  |  | 0 | 0%
7 | Integration & Testing
7.1 | Assemble rover | Team |  |  | 0 | 0%
7.2 | Subsystem testing | Team |  |  | 0 | 0%
7.3 | Software integration | Team |  |  | 0 | 0%
7.4 | Reliability testing | Team |  |  | 0 | 0%
8 | Competition Preparation
8.1 | Spare parts | Team |  |  | 0 | 0%
8.2 | Documentation | Team |  |  | 0 | 0%
8.3 | Packing | Team |  |  | 0 | 0%
8.4 | Final inspection | Team |  |  | 0 | 0%
8.5 | Competition | Team |  |  | 0 | 0%